# RWD Lineage Project Charter

RWD Lineage

Exported on 2026-03-16 10:38:31

Table of Contents

1	Table of Contents	3

2	Project Summary	4

2.1	Project Background	4

2.2	Project Objective	4

3	Project Scope	5

3.1	In Scope	5

3.2	Out of Scope	5

4	High-Level Deliverables	6

5	High-Level Assumptions & Constraints	7

5.1	Assumptions	7

5.2	Constraints	7

6	Project Milestone Summary	8

7	Communications	9

7.1	Internal Communications	9

7.2	External Communications	9

8	Project Stakeholders	10

8.1	RWD Lineage Team	10

8.2	Collaborations	12

9	References	13

10	Sub-milestones	14

# Table of Contents

- Table of Contents

- Project Summary

  - Project Background

  - Project Objective

- Project Scope

  - In Scope

  - Out of Scope

- High-Level Deliverables

- High-Level Assumptions & Constraints

  - Assumptions

  - Constraints

- Project Milestone Summary

- Communications

  - Internal Communications

  - External Communications

- Project Stakeholders

  - RWD Lineage Team

  - Collaborations

- References

# Project Summary

## Project Background

As part of FDA’s Framework for Real-World Evidence Program, FDA has been active in releasing industry guidance regarding the use of real-world data (RWD) and real-world evidence (RWE) in regulatory decision-making. Some key points included in this industry guidance include:

- SDTM is the accepted standard for FDA submissions, including RWE studies [1]

- Reliability (defined as accuracy, completeness, and traceability) of RWD is required to use RWE in regulatory decision-making [2]

- When evaluating completeness, accuracy, and plausibility of RWD, verification should be done against original source data [2]

- FDA must have access to records, including source RWD (e.g., original records in the EHR or as certified copies [3]

- Sponsors must submit patient-level data RWD that have been analyzed as part of the clinical study included in a marketing application; if certain RWD are owned and controlled by other entities, sponsors should have agreements in place with those entities to ensure that relevant patient-level data can be provided to FDA and that source data necessary to verify the RWD are made available for inspection [4]

Because of these requirements, additional lineage and traceability is needed to audit source data and quantify the information loss and performance of data transformations to generate reliable RWD in SDTM for regulatory use. This is because RWD like electronic health records (EHR), claims, etc., does not neatly align with SDTM domains, resulting in data loss during the complex processing steps that are required to transform source RWD to SDTM. This data loss results in unknown levels of unquantified errors that can introduce significant and unquantifiable biases (e.g. selection bias, misclassifications of outcomes and exposures) in the analysis dataset, causing data to be unreliable and precluding regulatory use of SDTM derived from RWD.

The RWD Lineage project aims to solve these issues when deriving SDTM from RWD. RWD Lineage will be a standardized and comprehensive representation of data lineage for each source patient data element that specifies either 1) the location of the element in the output SDTM dataset (Positive Lineage), or 2) that the element was not used in the output analysis dataset (Negative Lineage). RWD Lineage will be represented in a CDISC standard metadata model that supports using RWD in SDTM. This standardization will allow lineage to be combined across disparate data sources and will enable the unification of downstream tools, workflows, and analytics for validation and audit activities.

## Project Objective

The objective of this project is to create a machine-readable CDISC data exchange standard for lineage metadata that is supplied along with RWD-derived SDTM, which provides the data reliability required by FDA to use RWE as primary evidence.

# Project Scope

## In Scope

The items in scope for the initial release:

- Create a CDISC standard for lineage of SDTM derived from RWD

- Standard will be built to support RWE use cases involving submissions using RWE as primary evidence to regulators for decision-making, which includes (but is not limited to):

- External control arms (ECA)

- Prospectively collected RWD via EDC

- Pragmatic trials

- Validation studies

- Natural history studies

- Traceability and reliability of RWD sources that have been chosen for use in a study

- Support for RWD that includes secondary use data (e.g., EHR, medical claims, wearables, etc.)

## Out of Scope

The items that are out of scope* for the initial release:

- Support for non-CDISC data standards and common data models (e.g., FHIR, OMOP)

- Consideration of use cases for standards building that do not involve regulatory decision-making

- Traceability and reliability of RWD sources that are being assessed for potential use in a study (e.g., fit-for-purpose assessments of RWD)

- Support for synthetic/AI-generated data

*Out of scope items may be considered in the next phases of the project

# High-Level Deliverables

| - # | - Name | - Description |
| --- | --- | --- |
| - 1 | - RWD Lineage Model and Schema | - Data model and schema for the RWD Lineage standard managed in a CDISC GitHub repository (technical documentation). |
| - 2 | - RWD Lineage Specification | - Specification document for RWD Lineage authored in the CDISC Wiki and published in GitHub with GitHub pages (technical documentation). |
| - 3 | - RWD Lineage User/Implementation Guide | - A user guide that indicates the purpose and how the model can be used for different purposes. |
| - 4 | - RWD Lineage Examples | Examples that demonstrate RWD Lineage usage that are maintained in a CDISC GitHub repository. - End-to-end examples that will also demonstrate that the standard works |
| - 5 | - RWD Lineage Exchange Format | - A standard format in which RWD lineage information can be exchanged between systems based on the RWD lineage Model and Schema |

# High-Level Assumptions & Constraints

## Assumptions

- Existing CDISC standards may be suitable for modification as a starting point for the RWD Lineage standard (e.g., evaluate Define-XML or align with 360i)

## Constraints

- RWD Lineage should be compatible with current submission standards

- A low barrier for use and adoption and use by sponsors and regulators is essential

- Feasible for data sources (e.g., vendors) to implement

# Project Milestone Summary

| - # | - Project Milestone | - ETA |
| --- | --- | --- |
| - 1 | - Project scope completed | - November 2024 |
| - 2 | - Internal Review | - Q2 2026 |
| - 3 | - Public Review | - Q3 2026 |
| - 4 | - RWD Lineage Standard released | - Q4 2026 |

Sub-milestones

# Communications

## Internal Communications

RWD Lineage CDISC Wiki

## External Communications

| - # | - Communication Event or Task | - Target Date |
| --- | --- | --- |
| - 1 | - Circulate with the CDISC Advisory Council (CAC) for early buy-in once scope is finalized and agreed upon by the RWD Lineage team | - Q1 2025 |
| - 2 | - Share with FDA after incorporating CAC feedback and performing some preliminary work with extending the define.xml | - Q1 2025 |
| - 3 | - Present at a CDISC webinar to share the project scope and progress to date | - Q1 2025 |
| - 4 | - Present at a CDISC webinar to share the project scope and progress to date | - Q1 2025 |
| - 5 | - Present at the CDISC EU Interchange | - Q2 2025 |
| - 6 | - Present at the CDISC US Interchange | - Q4 2025 |
| - 7 | - Social media and blog posts | - Ongoing |
| - 8 | - Public Review webinar | - TBD |

# Project Stakeholders

## RWD Lineage Team

| - ID | - Name | - Company |
| --- | --- | --- |
| - 1 | - Sam Hume | - CDISC |
| - 2 | - Tasha Nagamine | - Droice Labs |
| - 3 | - Anita Umesh | - Genentech |
| - 4 | - Omar Garcia | - CDISC |
| - 5 | - Abhishek Dabral | - adabral |
| - 6 | - Adrienne Boyance | - Amgen |
| - 7 | - Aman Bahl |  |
| - 8 | - Amrita jha | - Icon clinical research |
| - 9 | - Ana Carmen Vazquez Martinez | - VAZTECH LVM |
| - 10 | - Areddy Prashanth | - Bayer |
| - 11 | - Ashwini Yermal Shanbhogue |  |
| - 12 | - Ayushi Agarwal | - Ephicacy Lifesciences Analytics Private Limited |
| - 13 | - Balachandran E | - Global Value Web Technologies Pvt Ltd |
| - 14 | - Berber Snoeijer | - ClinLine |
| - 15 | - Bhavleen Arora | - Bristol Myers Squibb |
| - 16 | - Brian Gillette | - Droice Labs |
| - 17 | - Choo Hyung Lee | - Daiichi Sankyo, Inc. |
| - 18 | - Christo Andonyadis | - NCI |
| - 19 | - Daniel Wanjiru | - Icon |
| - 20 | - Deep Bhattacharya | - Droice Labs |
| - 21 | - Deepthi Errabelly | - Merck |
| - 22 | - Devendran Maadu | - Global Value Web Technologies Pvt Ltd |
| - 23 | - Dhaval Patel | - SAS |
| - 24 | - Disheng Huang | - TechData |
| - 25 | - Gracy Crane | - Roche Pharmaceuticals |
| - 26 | - Harshit Saxena | - Droice Labs |
| - 27 | - Ingeborg Holt | - Orizaba Solutions |
| - 28 | - James | - Eda Clinical |
| - 29 | - Javier Rodriguez Soto | - OCS Life Sciences |
| - 30 | - Jeff Abolafia | - Pinnacle 21/Certara |
| - 31 | - Joe Xi | - Bristol Myers Squibb |
| - 32 | - John E |  |
| - 33 | - Joy Victor | - Merck |
| - 34 | - Kalpana Thakare Waghmare |  |
| - 35 | - Karen James | - Roche Diagnostics |
| - 36 | - Kim Yogin | - Daiichi Sankyo, Inc. |
| - 37 | - Kishore Pothuri | - Vita Global Sciences |
| - 38 | - Lakshmi Kubendran | - lobal Value Web |
| - 39 | - Lakshmi Mantha | - Ephicacy Life Sciences |
| - 40 | - Likhita Kolli | - GSK |
| - 41 | - Mike Gunshenan | - Takeda Pharmaceuticals |
| - 42 | - Matt Baldwin | - Amgen |
| - 43 | - Mayur Saxena | - Droice Labs |
| - 44 | - Mekhala Acharya | - Takeda Pharmaceuticals |
| - 45 | - Mike Hamidi | - Independent |
| - 46 | - Mike Kolzet | - EQTY Life Sciences |
| - 47 | - Natalie George | - Immatics |
| - 48 | - natraj Patro | - Boehringer Ingelheim |
| - 49 | - Ningappa Kanavi | - Accenture Pvt LTD |
| - 50 | - Pan Zonfming | - Amgen |
| - 51 | - Parag Shiralkar | - Sumptuous Data Sciences, LLC |
| - 52 | - Phillip Jackson | - IQVIA |
| - 53 | - Praveen C | - GSK |
| - 54 | - Prashanth Areddy | - Bayer |
| - 55 | - Purvi kalra | - Ephicacy Lifescience Analytics |
| - 56 | - Radhika Kale | - Bristol Myers Squibb |
| - 57 | - Rama Balakrishnan | - Roche |
| - 58 | - Rajat Jain | - Syneos Health |
| - 59 | - Rama Balakrishnan | - Roche |
| - 60 | - Ritika Sharma | - TCS |
| - 61 | - Roxanne Mirander | - GSK |
| - 62 | - Sandy VanPelt Nguyen | - Pfizer |
| - 63 | - Sarah Ferki |  |
| - 64 | - Sowmya Gabbula | - Astellas Pharma |
| - 65 | - Srinath Reddy | - Parexel |
| - 66 | - Susan Ko | - Verizon health |
| - 67 | - Sushma Ghanta |  |
| - 68 | - Trupti Kadgaonkar | - TCS |
| - 69 | - Umayal Annamalai |  |
| - 70 | - Venkata Ikkurthy | - Bayer |

## Collaborations

- CDISC Data Exchange Standards team

- PHUSE RWE Working Group

# References

- Data Standards for Drug and Biological Product Submissions Containing Real-World Data, December 2023

- Real-World Data: Assessing Electronic Health Records and Medical Claims Data To Support Regulatory Decision-Making for Drug and Biological Products, July 2024

- Use of Electronic Health Record Data in Clinical Investigations Guidance for Industry, July 2018

- Considerations for the Use of Real-World Data and Real-World Evidence To Support Regulatory Decision-Making for Drug and Biological Products, August 2023

- Transforming RWD for Regulatory Submissions: How to Use SDTM for RWD

# Sub-milestones

| - # | - Deliverable | - Status | - Due date | - Owner | - MIMIC Credentialing Required? |
| --- | --- | --- | --- | --- | --- |
| - 1 | - Scoping & requirements | - Done |  |  |  |
| - 1.1 | - RWD Lineage use cases | - Done |  |  |  |
| - 1.2 | - RWD Lineage scope | - Done |  |  |  |
| - 1.3 | - RWD Lineage requirements | - Done |  |  |  |
| - 2 | - SDTM implementation for use cases (ECA for Parkinson's disease; breast cancer) | - In progress |  |  |  |
| - 2.1 | - Study cohort generation | - Done |  | - Bala, Deep | - Yes |
| - 2.2 | - RWD study elements/output data requirements (required SDTM output + variables) | - In progress | - May 20, 2025 |  | - No |
| - 2.2 | - SDTM spec (Mapping specs) | - In progress |  | - Joy, Ashwini | - No |
| - 2.4 | - SDTM implementation (generation of code and programs) | - In progress |  | - Joy | - No |
| - 2.5 | - SDTM dataset generation | - In progress |  | - Joy | - Yes |
| - 3 | - Initial RWD Lineage model | - Not started |  |  |  |
| - 3.1 | - RWD Lineage entities/attributes | - Not started |  |  |  |
| - 3.2 | - Data model based on 3.1 | - Not started |  |  |  |
| - 3.3 | - RWD Lineage model in a data exchange format | - Not started |  |  |  |

e